## Sheet1
SI No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | 2026-02-16 | Database schema missing Twilio Call SID mapping for patient interactions | Sprint 1 | Backend Team | Data Model | Added call_sid column to interaction logs and updated schema | 2026-02-13 | Closed | Verified successfully
2 | 2026-03-02 | Patient Name speech recognition failing for non-English accents | Sprint 2 | Backend Team | Functional/NLU | Configured Twilio Gather to use speechModel with extended language hints | 2026-02-27 | Closed | Accuracy improved
3 | 2026-03-02 | Twilio webhook returning HTTP 422 for initial inbound calls | Sprint 2 | Integration Team | API Integration | Corrected FastAPI Pydantic schema validation for Twilio form-encoded payload | 2026-02-27 | Closed | Tested and verified
4 | 2026-03-16 | Twilio webhook returning HTTP 422 for initial inbound calls | Sprint 3 | Backend Team | Logic | Implemented 3-retry limit with graceful fallback to human agent | 2026-03-13 | Closed | Stable call session
5 | 2026-03-16 | SMS notifications failing for international patient phone numbers | Sprint 3 | Backend Team | Functional | Added E.164 format parsing and validation before triggering SMS API | 2026-03-15 | Closed | Validated via testing
6 | 2026-03-30 | Appointment scheduling allows double-booking for the same time slot | Sprint 4 | Backend Team | Logic | Added database transaction isolation lock when confirming slots | 2026-03-27 | Closed | Concurrency resolved
7 | 2026-03-30 | Doctor Review Queue API returning empty lists due to status flag bug | Sprint 4 | API Team | Backend | Fixed SQL query filter to correctly match 'pending_review' status | 2026-03-28 | Closed | Presentation-ready